## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nikita | 2026-01-16 | Movies already watched were appearing in recommendations | Sprint 2 | Nikita | Logical | Added filter to exclude previously rated movies | 2026-01-17 | Closed | Verified before Milestone 2 submission
2 | Nikita | 2026-01-26 | Cold-start users were not receiving recommendations | Sprint 3 | Nikita | Functional | Implemented popularity-based fallback logic | 2026-01-27 | Closed | Validated before Milestone 3 submission
3 | Nikita | 2026-02-09 | Login session was not persisting after refresh | Sprint 4 | Nikita | Functional | Improved session state management | 2026-02-09 | Closed | Confirmed stable before Milestone 4 completion

## Sheet2
Logical
User Interface
Maintainability
Standards
Others